## Totals
Pop up event estimate |  |  | Prepared by:
Date:
Materials |  |  | Fill-in
Event materials |  | Total cost
41.58
Management |  |  | 522.06
Venue |  |  | 854.7
Site |  |  | 697.62
Total cost
totals |  | total | 2115.96
(Subtotal)
Labor | Person hours |  | Fill-in
Event labor |  | Total==$25 X hrs | 605
Marketing labor | 52.8 |  | 1320
Producer | 24.2 |  | 605
Managers | 52.8 | Total==$25 X hrs | 1320
Venue staff | 23.1 | Total==$25 X hrs | 577.5
Site staff | 19.8 | Total==$25 X hrs | 495
Total labor | 172.7 | total cost | 4922.5
Subtotal
Totals |  | Break down chart | Fill-in
Total materials |  |  | 2115.96
Total man hours | 72.6
Total labor cost |  |  | 4922.5
Total cost |  |  | 7038.46

## schedule
Event planning |  |  | Prepared by: | PM Sue Brandt
Date:
Gantt Table
start date | End Date | task | duration
2023-06-01 | 2023-06-10 | Meet with clients | 9
2023-06-10 | 2023-08-10 | create marketing campaign | 61
2023-06-10 | 2023-06-17 | Planning Charts | 7
2023-06-21 | 2023-06-28 | site survey | 7
2023-06-10 | 2023-09-10 | Estimate costs | 92
2023-07-01 | 2023-09-05 | hire talent | 66
2023-06-21 | 2023-09-21 | Hire management staff | 92
2024-02-01 | 2024-05-02 | hire production staff | 91
2024-02-10 | 2024-06-01 | hire site staff | 112
2023-07-01 | 2024-01-10 | Management materials | 193
2023-07-01 | 2024-01-10 | Venue Materials | 193
2023-07-01 | 2024-06-01 | site materials | 336
2024-06-21 | 2024-07-01 | Load in | 10

## Producer labor
Campaign project PM |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Meet with clients | 1 | 6 | 6 | 25 | 150
create campaign | 1 | 8 | 8 | 25 | 200
hire team | 1 | 4 | 4 | 25 | 100
research costs | 1 | 4 | 4 | 25 | 100
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 22 |  | 550
|  | 10% Contingency: | 2.2 |  | 55
|  | Total: | 24.2 |  | 605
2020-06-01 | Meet with clients | 6
2020-06-01 | create campaign | 3
2020-06-02 | hire team | 6
2020-06-02 | research costs | 4
2020-06-14 | buy add | 2
2020-06-16 | launch add | 5
2020-06-25 | event launch | 1
2020-06-26 | collect date | 1

## Marketing labor
Marketing |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meet with client | 1 | 1 | 0 | 25 | 0
write copy | 1 | 1 | 1 | 25 | 25
create image | 1 | 1 | 1 | 25 | 25
create merge copy and image | 1 | 1 | 1 | 25 | 25
|  |  | 0 | 25 | 0
write copy | 1 | 1 | 1 | 25 | 25
create video | 4 | 4 | 16 | 25 | 400
|  |  | 0 | 25 | 0
obtain logo | 1 | 3 | 3 | 25 | 75
|  |  | 0 | 25 | 0
merge logo on all content | 1 | 3 | 3 | 25 | 75
buy image ad | 1 | 3 | 3 | 25 | 75
buy video ad | 1 | 3 | 3 | 25 | 75
collect data | 1 | 16 | 16 | 25 | 400
|  |  | 0 | 25 | 0
|  | Subtotal: | 48 |  | 1200
|  | 10% Contingency: | 4.8 |  | 120
|  | Total: | 52.8 |  | 1320

## Marketing Materials
Marketing Materials |  |  | Prepared by: | PM Sue Brandt
Channel costs |  |  | Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
1 |  | facebook | 12 | 12
1 |  | google | 12 | 12
1 |  | Tiktok | 12 | 12
|  | Instagram |  | 0
|  | Linkedin |  | 0
|  | Website |  | 0
0
0
0
0
0
0
0
|  |  | Subtotal: | 36
|  |  | 5% Hardware Estimate: | 1.8
|  |  | Subtotal: | 37.8
|  |  | 10% Contingency: | 3.78
|  |  | Total: | 41.58

## Management materals
Management Materials |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
1 | ea | binder | 2 | 2
15 | ea | board games | 30 | 450
0
0
0
0
0
0
|  |  | Subtotal: | 452
|  |  | 5% Hardware Estimate: | 22.6
|  |  | Subtotal: | 474.6
|  |  | 10% Contingency: | 47.46
|  |  | Total: | 522.06

## Managers labor
Preproduction labor |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Meet with clients | 1 | 2 | 2 | 25 | 50
build team | 1 | 2 | 2 | 25 | 50
hire team | 1 | 2 | 2 | 25 | 50
design event space | 1 | 16 | 16 | 25 | 400
find venue | 1 | 16 | 16 | 25 | 400
research costs | 1 | 4 | 4 | 25 | 100
buy materials | 1 | 4 | 4 | 25 | 100
build booth | 1 | 2 | 2 | 25 | 50
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 48 |  | 1200
|  | 10% Contingency: | 4.8 |  | 120
|  | Total: | 52.8 |  | 1320

## Venue materials
Venue Materials |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
45 | ea | chairs | 2 | 90
10 | ea | tables | 10 | 100
10 | ea | table clothes | 25 | 250
1 | group | food | 200 | 200
1 | group | drink | 100 | 100
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 740
|  |  | 5% Hardware Estimate: | 37
|  |  | Subtotal: | 777
|  |  | 10% Contingency: | 77.7
|  |  | Total: | 854.7

## Venue labor
Venue llabor |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
load in. | 2 | 2 | 4 | 25 | 100
set up | 2 | 2 | 4 | 25 | 100
test | 1 | 1 | 1 | 25 | 25
run event | 1 | 6 | 6 | 25 | 150
close | 2 | 1 | 2 | 25 | 50
strike | 2 | 2 | 4 | 25 | 100
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 21 |  | 525
|  | 10% Contingency: | 2.1 |  | 52.5
|  | Total: | 23.1 |  | 577.5

## Site labor
Site labor |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meeting | 4 | 2 | 8 | 25 | 200
rebuild | 4 | 2 | 8 | 25 | 200
store gear | 2 | 1 | 2 | 25 | 50
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 18 |  | 450
|  | 10% Contingency: | 1.8 |  | 45
|  | Total: | 19.8 |  | 495

## Site materials
Site materials |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
2 | ea | binder | 2 | 4
3 | ea | storate | 200 | 600
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 604
|  |  | 5% Hardware Estimate: | 30.2
|  |  | Subtotal: | 634.2
|  |  | 10% Contingency: | 63.42
|  |  | Total: | 697.62

## Online social media list
Campaign project |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | ad | Unit Cost | Extended Cost | Source
1 |  | facebook
1 |  | google
1 |  | linked in
1 |  | twitter
1 |  | tiktok
1 |  | instagram
1
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0