## Totals sheet
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Materials build and paint |  |  | Fill-in
transferring data teaching website
AV materials |  | Total cost | 0 |  | http://ccm.net/faq/9795-transfer-data-between-excel-spreadsheets
Display materials |  | Total cost | 0
scenic and paint |  | total | 0
(Subtotal)
Build Labor | Person hours |  | Fill-in
Technical Director | 103.4 | Total==$40 X hrs | 4149.2
AV labor | 0 | Total==$20 X hrs | 0
Display labor | 0 | Total==$20 X hrs | 0
Total labor | 103.4 | total cost | 4149.2
Subtotal
Totals |  | Break down chart | Fill-in
Total materials |  |  | 0
Total man hours | 103.4
Total labor cost |  |  | 4149.2
Total cost |  |  | 4149.2

## schedule
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Gantt Table
start date | task | duration
2020-06-01 | Meet with clients | 6
2020-06-01 | Draw and plan | 3
2020-06-02 | hire team | 6
2020-06-02 | order materials | 4
2020-06-14 | supervise team load in | 2
2020-06-16 | Supetvise team tech | 5
2020-06-25 | supervise one day run | 1
2020-06-26 | supervise load out | 1

## AV materials
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost | Source
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## AV labor labor
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
l |  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## Display materials
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## Display labor
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 2 | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## TD labor
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Meet with clients | 1 | 6 | 6 | 40 | 240
Draw and plan | 1 | 8 | 8 | 40 | 320
hire team | 1 | 4 | 4 | 40 | 160
order materials | 1 | 4 | 4 | 41 | 164
supervise team load in | 1 | 16 | 16 | 40 | 640
supervise team tech | 1 | 40 | 40 | 40 | 1600
supervise team one day run | 1 | 8 | 8 | 40 | 320
supervise team load out | 1 | 8 | 8 | 41 | 328
|  | Subtotal: | 94 |  | 3772
|  | 10% Contingency: | 9.4 |  | 377.2
|  | Total: | 103.4 |  | 4149.2
2020-06-01 | Meet with clients | 6
2020-06-01 | Draw and plan | 3
2020-06-02 | hire team | 6
2020-06-02 | order materials | 4
2020-06-14 | supervise team load in | 2
2020-06-16 | Supetvise team tech | 5
2020-06-25 | supervise one day run | 1
2020-06-26 | supervise load out | 1

## Available materials
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost | Source
4 | ea | flat screen monitors 60" | 120 | 480 | Gaming company owns
6 | ea | Elgato Stream deck | 150 | 900 | Gaming company owns
6 | ea | Lenovo PC | 800 | 4800 | Gaming company owns
6 | ea | USB audio Adapter | 14 | 84 | Gaming company owns
1 | ea | head phones | 100 | 100 | Gaming company owns
4 | ea | PC mic | 100 | 400 | Gaming company owns
4 | ea | XLR to mini adapter | 15 | 60 | Gaming company owns
6 | ea | HDMI to HDMI mini | 25 | 150 | Gaming company owns
6 | ea | Hyperdrive USB C hub | 100 | 600 | Gaming company owns
6 | ea | HDMI mini to USB C | 16 | 96 | Gaming company owns
10 | ea | power strips with surge protection | 20 | 200 | Gaming company owns
10 | ea | edison power cables 20 amp | 25 | 250 | Gaming company owns
4 | ea | speakers | 600 | 2400 | Gaming company owns
4 | ea | ultimate stands | 200 | 800 | Gaming company owns
4 | ea | speakon cable | 100 | 400 | Gaming company owns
1 | ea | sound mixer | 350 | 350 | Gaming company owns
8 | ea | XLR cable 25'-0" | 30 | 240 | Gaming company owns
2 | ea | Projector | 500 | 1000 | Gaming company owns
2 | ea | HDMI cable 30' | 100 | 200 | Gaming company owns
1 | ea | Video switcher | 400 | 400 | Gaming company owns
6 | ea | table 3x6 | 40 | 240 | Gaming company owns
5 | ea | table clothes fitted | 60 | 300 | Gaming company owns
16 | ea | truss: 12 box 8 ft tall | 300 | 4800 | Gaming company owns
2 | ea | truss: 12" box 8 ft tall | 300 | 600 | Gaming company owns
1 | ea | truss hardward | 200 | 200 | Gaming company owns
4 | ea | Truss base | 200 | 800 | Gaming company owns
2 | ea | Projector mount to truss | 100 | 200 | Gaming company owns
2 | ea | RP screen | 400 | 800 | Gaming company owns
1 | ea | bubble wrap | 150 | 150 | Gaming company owns
5 | ea | road box | 100 | 500 | Gaming company owns
2 | ea | glass cleaner | 20 | 40 | Gaming company owns
12 | ea | wipes | 20 | 240 | Gaming company owns
16 | ea | stanchions | 150 | 2400 | Gaming company owns
15 | ea | stanchion ropes | 200 | 3000 | Gaming company owns
1 | box | COVID signs and stickers | 100 | 100 | Gaming company owns
5 | ea | Camera Tripod | 25 | 125 | Gaming company owns
0
|  |  | Subtotal: | 28405
|  |  | 5% Hardware Estimate: | 1420.25
|  |  | Subtotal: | 29825.25
|  |  | 10% Contingency: | 2982.525
|  |  | Total: | 32807.775