## Totals sheet
Materials Part 1 |  | Amount | calculated
gaming company purchases |  | Total cost | 32807.78 | transferring data teaching website
load in materials |  | Total cost | 0 | http://ccm.net/faq/9795-transfer-data-between-excel-spreadsheets
Tech materials |  | Total cost | 0
load out materials |  | Total cost | 0
subtotal |  | total | 32807.78
Crew labor Part 1 | Person hours | Amount | calculated
load in | 0 | Total==$20 X hrs | 0
tech | 0 | Total==$20 X hrs | 660
load out | 0 | Total==$20 X hrs | 0
| 0 | total | 660
TD Labor costs Part 1 | Person hours | Amount | calculated
Technical Director part 1 labor | 103.4 | Total==$40 X hrs | 4160.2
TD load out voorhees labor | 8.8 | Total==$40 X hrs | 352
| 112.2 | total cost | 4512.2
Tour labor Part 2 | Person hours |  | calculated
Voorhees | 0 |  | 0
New Theatre lobby (City Tech) | 0 |  | 0
Park Slope event space | 0 |  | 0
HERE ARTS Center | 0 |  | 0
Signature Theatre Lobby | 0 |  | 0
St Johns, Stamford Ct Lawn | 0 |  | 0
| 0 | Subtotal | 0
Part 3 Obstacle | Person hours |  | calculated
materials |  |  | 0
Labor | 0 |  | 0
Subtotal
Totals
total materials costs | Person hours |  | 32807.78
Total labor costs | 112.2 |  | 5172.2
|  | Total | 37979.98

## gant
Gaming Tour 2020 |  | Production Manager Sue Brandt
task | start date | end date | duration
game development | 2020-04-01 | 2020-04-13 | 12
Tour display design | 2020-04-07 | 2020-04-13 | 6
soft test with local gear | 2020-04-08 | 2020-04-13 | 5
order materials | 2020-04-15 | 2020-04-18 | 3
build electrical system | 2020-04-21 | 2020-04-27 | 6
build sound and light sytem | 2020-04-21 | 2020-04-27 | 6
build game system | 2020-04-21 | 2020-04-27 | 6
test game system | 2020-04-25 | 2020-04-27 | 2
test sound and lights | 2020-04-25 | 2020-04-27 | 2
integrate systems | 2020-04-28 | 2020-05-01 | 3
soft opening gaming session | 2020-05-01 | 2020-05-02 | 1
prep gear for tour | 2020-05-05 | 2020-05-09 | 4
load truck | 2020-05-10 | 2020-05-11 | 1
unload truck | 2020-05-14 | 2020-05-15 | 1
load in event | 2020-05-14 | 2020-05-15 | 1
tech event | 2020-05-14 | 2020-05-15 | 1
run event | 2020-05-14 | 2020-05-15 | 1
Tour schedule | open | close | Duration | Crew
Voorhees | 2020-05-14 | 2020-05-16 | 2 | non-union
New Theatre lobby (City Tech) | 2020-05-18 | 2020-05-21 | 3 | non-union
Park Slope event space | 2020-05-22 | 2020-05-25 | 3 | Union
HERE ARTS Center | 2020-05-26 | 2020-05-29 | 3 | Union
Signature Theatre Lobby | 2020-05-30 | 2020-06-03 | 4 | Union
St Johns, Stamford Ct Lawn | 2020-06-04 | 2020-06-08 | 4 | non-union
Location | Address
Voorhees | 186 Jay St Brooklyn NY 11201
New Theatre lobby (City Tech) | 300 Jay St Brooklyn NY 11201
Park Slope event space | 164 20th St, Brooklyn 11232
HERE ARTS Center | 145 6th Ave, New York NY 10013
Signature Theatre Lobby | 480 42nd st, NY NY 10036
St Johns, Stamford Ct Lawn | 884 Newfield Ave, Stamford Ct 06905

## TD labor
Gaming project
|  | Prepared by: | TD
|  | Date: | 2020-04-02
|  | TD labor | 40
Procedure: | date | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meet with client | 2020-04-01 | 1 | 3 | 3 | 40 | 120
preparing bid documents | 2020-04-02 | 1 | 6 | 6 | 41 | 246
hire crew | 2020-04-03 | 1 | 8 | 8 | 42 | 336
Tour display design | 2020-04-07 | 1 | 6 | 6 | 40 | 240
soft test with local gear | 2020-04-08 | 1 | 6 | 6 | 40 | 240
order materials | 2020-04-15 | 1 | 2 | 2 | 40 | 80
build electrical system | 2020-04-21 | 1 | 8 | 8 | 40 | 320
build sound and light sytem | 2020-04-21 | 1 | 2 | 2 | 40 | 80
build game system | 2020-04-21 | 1 | 8 | 8 | 40 | 320
test game system | 2020-04-25 | 1 | 8 | 8 | 40 | 320
test sound and lights | 2020-04-25 | 1 | 2 | 2 | 40 | 80
integrate systems | 2020-04-28 | 1 | 4 | 4 | 40 | 160
soft opening gaming session | 2020-05-01 | 1 | 4 | 4 | 40 | 160
prep gear for tour | 2020-05-05 | 1 | 8 | 8 | 40 | 320
load truck | 2020-05-10 | 1 | 2 | 2 | 40 | 80
unload truck | 2020-05-14 | 1 | 2 | 2 | 40 | 80
load in event | 2020-05-14 | 1 | 4 | 4 | 40 | 160
tech event | 2020-05-14 | 1 | 3 | 3 | 40 | 120
run event | 2020-05-14 | 1 | 8 | 8 | 40 | 320
|  |  |  | 0 | 40 | 0
|  |  |  | 0 | 40 | 0
|  |  |  | 0 | 40 | 0
|  |  |  | 0 | 40 | 0
|  |  |  | 0 | 40 | 0
|  |  | Subtotal: | 94 |  | 3782
|  |  | 10% Contingency: | 9.4 |  | 378.2
|  |  | Total: | 103.4 |  | 4160.2

## TD load out labor
Gaming project
| Prepared by: | TD
Date:
load out labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
truck pack planning | 1 | 2 | 2 | 40 | 80
supervise crew | 1 | 4 | 4 | 40 | 160
park truck at secure locations | 1 | 2 | 2 | 40 | 80
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  |  | 0 | 40 | 0
|  | Subtotal: | 8 |  | 320
|  | 10% Contingency: | 0.8 |  | 32
|  | Total: | 8.8 |  | 352

## Game Co Materials
Gaming Project |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost | Source
4 | ea | flat screen monitors 60" | 120 | 480 | Gaming company owns
6 | ea | Elgato Stream deck | 150 | 900 | Gaming company owns
6 | ea | Lenovo PC | 800 | 4800 | Gaming company owns
6 | ea | USB audio Adapter | 14 | 84 | Gaming company owns
1 | ea | head phones | 100 | 100 | Gaming company owns
4 | ea | PC mic | 100 | 400 | Gaming company owns
4 | ea | XLR to mini adapter | 15 | 60 | Gaming company owns
6 | ea | HDMI to HDMI mini | 25 | 150 | Gaming company owns
6 | ea | Hyperdrive USB C hub | 100 | 600 | Gaming company owns
6 | ea | HDMI mini to USB C | 16 | 96 | Gaming company owns
10 | ea | power strips with surge protection | 20 | 200 | Gaming company owns
10 | ea | edison power cables 20 amp | 25 | 250 | Gaming company owns
4 | ea | speakers | 600 | 2400 | Gaming company owns
4 | ea | ultimate stands | 200 | 800 | Gaming company owns
4 | ea | speakon cable | 100 | 400 | Gaming company owns
1 | ea | sound mixer | 350 | 350 | Gaming company owns
8 | ea | XLR cable 25'-0" | 30 | 240 | Gaming company owns
2 | ea | Projector | 500 | 1000 | Gaming company owns
2 | ea | HDMI cable 30' | 100 | 200 | Gaming company owns
1 | ea | Video switcher | 400 | 400 | Gaming company owns
6 | ea | table 3x6 | 40 | 240 | Gaming company owns
5 | ea | table clothes fitted | 60 | 300 | Gaming company owns
16 | ea | truss: 12 box 8 ft tall | 300 | 4800 | Gaming company owns
2 | ea | truss: 12" box 8 ft tall | 300 | 600 | Gaming company owns
1 | ea | truss hardward | 200 | 200 | Gaming company owns
4 | ea | Truss base | 200 | 800 | Gaming company owns
2 | ea | Projector mount to truss | 100 | 200 | Gaming company owns
2 | ea | RP screen | 400 | 800 | Gaming company owns
1 | ea | bubble wrap | 150 | 150 | Gaming company owns
5 | ea | road box | 100 | 500 | Gaming company owns
2 | ea | glass cleaner | 20 | 40 | Gaming company owns
12 | ea | wipes | 20 | 240 | Gaming company owns
16 | ea | stanchions | 150 | 2400 | Gaming company owns
15 | ea | stanchion ropes | 200 | 3000 | Gaming company owns
1 | box | COVID signs and stickers | 100 | 100 | Gaming company owns
5 | ea | Camera Tripod | 25 | 125 | Gaming company owns
$ -
|  |  | Subtotal: | 28405
|  |  | 5% Hardware Estimate: | 1420.25
|  |  | Subtotal: | 29825.25
|  |  | 10% Contingency: | 2982.53
|  |  | Total: | 32807.78

## Load In Materials
Gaming project
Project
Prepared by:
Date:
load in materials
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## Tech materials
Gaming project
Prepared by:
Date:
Tech
Quantity | Unit | Material | Unit Cost | Extended Cost
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## load out materials
Gaming project
Prepared by:
Date:
ELEMENT: | load out
Quantity | Unit | Material | Unit Cost | Extended Cost
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
|  |  | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## crew load in labor
Gaming project
Prepared by:
Date:
ELEMENT: | load in labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## crew TECH labor
Gaming project
Project
| Prepared by: | Edsel Torres
Date:
ELEMENT: | Tech labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Audio Tech | 2 | 4 | 8 | 30 | 240
Video Tech | 2 | 4 | 8 | 30 | 240
Stage Hand | 1 | 4 | 4 | 30 | 120
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  |  | 0 | 20 | 0
|  | Subtotal: | 20 |  | 600
|  | 10% Contingency: | 2 |  | 60
|  | Total: | 22 |  | 660

## crew load out labor
Gaming project
Project
Prepared by:
Date:
ELEMENT: | Tech labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## load in non union example
Gaming project
Prepared by:
non union load in estimate | Date:
load in labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
tape out location | 2 | 1 | 2 | 20 | 40
unload truck | 4 | 2 | 8 | 20 | 160
build screen truss units | 2 | 1 | 2 | 20 | 40
install truss | 4 | 1 | 4 | 20 | 80
install and focus truss projectors | 1 | 1 | 1 | 20 | 20
Focus projectors | 1 | 1 | 1 | 20 | 20
install table | 2 | 1 | 2 | 20 | 40
install gaming system | 2 | 2 | 4 | 20 | 80
install sound system | 2 | 2 | 4 | 20 | 80
Test game | 2 | 1 | 2 | 20 | 40
integrate audio and projecct and control | 3 | 1 | 3 | 20 | 60
run test game | 2 | 1 | 2 | 20 | 40
notes | 3 | 1 | 3 | 20 | 60
open attraction | 2 | 1 | 2 | 20 | 40
|  |  | 0 | 20 | 0
|  | Subtotal: | 40 |  | 800
|  | 10% Contingency: | 4 |  | 80
|  | Total: | 44 |  | 880

## load in union example
| Prepared by: | Sue Brandt Production Manager
Union crew Estimate | Date: | 2020-04-19
load in labor
Procedure: Load-in | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Pink card employee earn $250.00 per day regardless of hours | 2 | 1 | 2 | 250 | 500 | rates
Union 101 crew head | 1 | 8 | 8 | 45 | 360 | Crewhead | 45 | hour
| 2 | 1 | 2 | 20 | 40 | stagehand | 30 | hour
tape out location 1 pink card, 1 stagehand | 1 | 1 | 1 | 30 | 30 | Teamster | 25 | hour
[5 empty] | 0 | Pinkcard | 250 | day
unload truck 1 pink card 3 teamsters | 3 | 2 | 6 | 25 | 150
build screen truss units 1 pink card 1 stagehand | 1 | 1 | 1 | 30 | 30
install truss 1 pink card 2 stagehand | 3 | 1 | 3 | 30 | 90
install and focus truss projectors 1 pinkcard 2 stagehands | 2 | 1 | 2 | 30 | 60
Focus projectors 1 pinkcard 2 stagehand | 2 | 1 | 2 | 30 | 60
install table 1 pinkcard 2 stagehand | 2 | 1 | 2 | 30 | 60
install gaming system 1 pinkcard 2 stagehand | 2 | 2 | 4 | 30 | 120
Test game 2 pink card | 2 | 1 | 2 | 0 | 0
integrate audio and projecct and control 2 pink card | 2 | 1 | 2 | 0 | 0
run test game 2 pink card | 2 | 1 | 2 | 0 | 0
notes 1 pinkcard 2 stagehand | 2 | 1 | 2 | 30 | 60
Train run crew 2 pink card 2 stagehands | 2 | 1 | 2 | 30 | 60
open attraction 1 pink card and 2 stagehands | 2 | 8 | 16 | 30 | 480
|  |  | 0 |  | 0
|  | Subtotal: | 49 |  | 1240
|  | 10% Contingency: | 4.9 |  | 124
|  | Total: | 53.9 |  | 1364

## voorhees
Gaming project
Prepared by:
Date:
ELEMENT: | load in labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## new theatre lobby
Gaming project
Prepared by:
Date:
load in labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## park slope
| Prepared by: | Sue Brandt Production Manager
Union crew Estimate | Date: | 2020-04-19
load in labor
Procedure: Load-in | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 |  | 0 | rates
|  |  | 0 |  | 0 | Crewhead | 45 | hour
|  |  | 0 |  | 0 | stagehand | 30 | hour
|  |  | 0 |  | 0 | Teamster | 25 | hour
|  |  | 0 |  | 0 | Pinkcard | 250 | day
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## here
| Prepared by: | Sue Brandt Production Manager
Union crew Estimate | Date: | 2020-04-19
load in labor
Procedure: Load-in | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 |  | 0 | rates
|  |  | 0 |  | 0 | Crewhead | 45 | hour
|  |  | 0 |  | 0 | stagehand | 30 | hour
|  |  | 0 |  | 0 | Teamster | 25 | hour
|  |  | 0 |  | 0 | Pinkcard | 250 | day
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0 |  |  |  | her
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## signature
| Prepared by: | Sue Brandt Production Manager
Union crew Estimate | Date: | 2020-04-19
load in labor
Procedure: Load-in | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
[5 empty] | 0 | rates
|  |  | 0 |  | 0 | Crewhead | 45 | hour
|  |  | 0 |  | 0 | stagehand | 30 | hour
|  |  | 0 |  | 0 | Teamster | 25 | hour
|  |  | 0 |  | 0 | Pinkcard | 250 | day
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## church
Gaming project
Prepared by:
Date:
ELEMENT: | load in labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## Obstacle materials
Gaming project
Prepared by:
Date:
obstacle materials
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## Obstacle labor
Gaming project
Project
| Prepared by: | Edsel Torres
Date:
obstacle labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0