Contents

[Diagram 1](#_Toc51249612)

[Outline 1](#_Toc51249613)

[Dictionary 2](#_Toc51249614)

# WBS Diagram for Birthday party

# Outline

1 Party planning

* + - * 1.1 Layout
        + 1.1.1 Draw ground plan
        + 1.1.2 Add Jedi training area layer
        + 1.1.3 Add paper airplane flight area layer
        + 1.1.4 Add food area
        + 1.1.5 Add safety areas
      * 1.2 Hire talent for Jedi training
        + 1.2.1 check Brandt network of actors
        + 1.2.1.1 check www
        + 1.2.1.2 talent inquiries
        + 1.2.1.3 interpret collected information
        + 1.2.2 offer actors’ job
        + 1.2.2.1 sign contracts
      * 1.3 Paper airplanes
        + 1.3.1 research paper folding
        + 1.3.2 test designs
        + 1.3.3 Teach team
      * 1.4 Food
        + 1.4.1 Create menu
        + 1.4.2 estimate food
        + 1.4.3 finalize menu
        + 1.4.4 order food
      * 1.5 Marketing
        + 1.5.1. create online invitation
        + 1.5.2 Create invite list
        + 1.5.3 count participants

# Dictionary

**Party planning**- Plan for fun Star Wars themed birthday party for Emily

**Layout**- The documentation to present the display locations of all elements of event in a rental space. The document will include a ground plan to share with facility. The document will include separate layers to demonstrate play areas, food areas and fire lanes for crowd management. The diagrams will include all play areas needed to support the game playing experience for the children and their parents; insuring safety for all in attendance.

**Hire Talent**- Define characters and hire actors to play roles and entertain the guests.

**Food**- Appropriate types and quantities of food and drink for all guests

**Paper airplanes**-. Creation of airplanes with kid interaction and experience for best practice of game play and audience experience.

**Marketing**- Invitation of kids and their families to the event with a goal of 30 kids participating in the game play.