Add a level to Among US

|  |  |  |  |
| --- | --- | --- | --- |
| **Activity No** | **Activity/task description** | **Expected completion time** | **Dependency** |
| 1. | Define Scope of project | 3 | **-** |
| 2. | Define Deliverables | 3 | 1 |
| 3. | Establish assets | 7 | 1,2 |
| 4. | Ground plan design | 7 | 2,3 |
| 5. | 3-character upgrades | 6 | 3 |
| 6. | 2-mini games | 5 | 3,4 |
| 7. | Test until working | 10 | 4,5,6 |
| 8. | Present proof of concept to client | 2 | 7 |

BOILER PROJECT PERT CHART TABLE

|  |  |  |  |
| --- | --- | --- | --- |
| **Task** | **Description** | **Estimated duration (hrs.)** | **Dependency** |
| 1 | View boiler |  |  |
| 2 | System design |  |  |
| 3 | Build plan |  |  |
| 4 | Materials procurement |  |  |
| 5 | Build frame |  |  |
| 6 | Paint |  |  |
| 7 | Build power system |  |  |
| 8 | Build effects |  |  |
| 9 | Install electrical system |  |  |
| 10 | Test |  |  |
| 11 | Touch up |  |  |
| 12 | Deliver |  |  |