## Totals sheet
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Week 1
Game development
Team
Project Manager
Developer
Coder
IT system Management
Graphic artists
Materials Part 1 |  | Amount | calculated
gaming company purchases |  | Total cost | 32807.78
IT materials |  | Total cost | 0
Game development materials |  | Total cost
subtotal |  | total | 32807.78
Game development labor | Person hours | Amount | calculated
IT Labor development | 0 | Total==$20 X hrs | 0
Game Dev Labor | 0 | Total==$20 X hrs | 0
| 0 | total | 0
Tour company
TD Labor costs Part 1 | Person hours | Amount | calculated
Technical Director part 1 labor | 103.4 | Total==$40 X hrs | 2585
TD load out voorhees labor | 8.8 | Total==$40 X hrs | 220
| 112.2 | total cost | 2805
Final project
Weekly update costs | Person hours |  | calculated
Voorhees | 0 |  | 0
New Theatre lobby (City Tech) | 0 |  | 0
Park Slope event space | 0 |  | 0
HERE ARTS Center | 0 |  | 0
Signature Theatre Lobby | 0 |  | 0
St Johns, Stamford Ct Lawn | 0 |  | 0
| 0 | Subtotal | 0
Final project
Part 3 Obstacle | Person hours |  | calculated
materials |  |  | 0
Labor | 0 |  | 0
Subtotal
Updates for each project
Totals
total materials costs | Person hours |  | 32807.78
Total labor costs | 112.2 |  | 2805
|  | Total | 35612.78

## Deliverables
Timeline
November September 1 through Oct 31 2022
Job titles | Responcibilities
Project Manager
Developer
programmer/Coder
Graphic artist
IT system Manager
Deliverables
1 | 1 new map, 6 rooms
2 | 3 new mini games
3 | 4 new hats
Project Manager
Developer
programmer/Coder
Graphic artist
IT system Manager
Tasks | Start date | end date | total
Meet with client | 2022-09-01 | 2022-09-02 | 1
define deliverables | 2022-09-02 | 2022-09-05 | 3
assign asset responcibilities | 2022-09-05 | 2022-09-06 | 1
new map | 2022-09-06 | 2022-09-20 | 14
mini games | 2022-09-06 | 2022-09-20 | 14
hats | 2022-09-06 | 2022-09-20 | 14
demo of assets | 2022-09-21 | 2022-09-25 | 4
merge assets with new map | 2022-09-25 | 2022-09-28 | 3
test | 2022-10-01 | 2022-10-10 | 9
update | 2022-10-04 | 2022-10-12 | 8
deliver proof of concept | 2022-10-14 | 2022-10-15 | 1
upload to among us server | 2022-10-15 | 2022-10-16 | 1
test | 2022-10-17 | 2022-10-28 | 11
update | 2022-10-18 | 2022-10-29 | 11
open new map to play locally | 2022-10-30 | 2022-10-31 | 1

## Tour gant
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
| Gaming Tour 2020 | Installation development and launch | Production Manager Sue Brandt
| task | start date | end date | duration
| game development | 2020-04-01 | 2020-04-13 | 12
| Tour display design | 2020-04-07 | 2020-04-13 | 6
| soft test with local gear | 2020-04-08 | 2020-04-13 | 5
| order materials | 2020-04-15 | 2020-04-18 | 3
| build electrical system | 2020-04-21 | 2020-04-27 | 6
| build sound and light sytem | 2020-04-21 | 2020-04-27 | 6
| build gaming setup | 2020-04-21 | 2020-04-27 | 6
| test gaming setup | 2020-04-25 | 2020-04-27 | 2
| test sound and lights | 2020-04-25 | 2020-04-27 | 2
| integrate systems | 2020-04-28 | 2020-05-01 | 3
| soft opening gaming session | 2020-05-01 | 2020-05-02 | 1
| prep gear for tour | 2020-05-05 | 2020-05-09 | 4
| load truck | 2020-05-10 | 2020-05-11 | 1
| unload truck | 2020-05-14 | 2020-05-15 | 1
| load in event | 2020-05-14 | 2020-05-15 | 1
| tech event | 2020-05-14 | 2020-05-15 | 1
| run event | 2020-05-14 | 2020-05-15 | 1
ENT Tour schedule
| Tour schedule | open | close | Duration | Crew
| Voorhees | 2020-05-14 | 2020-05-16 | 2 | non-union
| New Theatre lobby (City Tech) | 2020-05-18 | 2020-05-21 | 3 | non-union
| Park Slope event space | 2020-05-22 | 2020-05-25 | 3 | Union
| HERE ARTS Center | 2020-05-26 | 2020-05-29 | 3 | Union
| Signature Theatre Lobby | 2020-05-30 | 2020-06-03 | 4 | Union
| St Johns, Stamford Ct Lawn | 2020-06-04 | 2020-06-08 | 4 | non-union
| Location | Address
| Voorhees | 186 Jay St Brooklyn NY 11201
| New Theatre lobby (City Tech) | 300 Jay St Brooklyn NY 11201
| Park Slope event space | 164 20th St, Brooklyn 11232
| HERE ARTS Center | 145 6th Ave, New York NY 10013
| Signature Theatre Lobby | 480 42nd st, NY NY 10036
| St Johns, Stamford Ct Lawn | 884 Newfield Ave, Stamford Ct 06905
Emerging weekly game update plan
Gaming Team GANT
Description |  | update | download | Duration
Weekly updates | Voorhees | 2022-04-11 | 2022-04-14 | 3
| New Theatre lobby (City Tech) | 2022-04-25 | 2022-04-28 | 3
| Park Slope event space | 2022-05-02 | 2022-05-05 | 3
| HERE ARTS Center | 2022-05-09 | 2022-05-12 | 3
| Signature Theatre Lobby | 2022-05-16 | 2022-05-19 | 3
| St Johns, Stamford Ct Lawn | 2022-05-30 | 2022-06-02 | 3

## IT materials
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Tech
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## IT labor planning
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## Game Dev Labor planning
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0

## Tour Co display Materials
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Quantity | Unit | Material | Unit Cost | Extended Cost | Source
4 | ea | flat screen monitors 60" | 120 | 480 | Gaming company owns
6 | ea | Elgato Stream deck | 150 | 900 | Gaming company owns
6 | ea | Lenovo PC | 800 | 4800 | Gaming company owns
6 | ea | USB audio Adapter | 14 | 84 | Gaming company owns
1 | ea | head phones | 100 | 100 | Gaming company owns
4 | ea | PC mic | 100 | 400 | Gaming company owns
4 | ea | XLR to mini adapter | 15 | 60 | Gaming company owns
6 | ea | HDMI to HDMI mini | 25 | 150 | Gaming company owns
6 | ea | Hyperdrive USB C hub | 100 | 600 | Gaming company owns
6 | ea | HDMI mini to USB C | 16 | 96 | Gaming company owns
10 | ea | power strips with surge protection | 20 | 200 | Gaming company owns
10 | ea | edison power cables 20 amp | 25 | 250 | Gaming company owns
4 | ea | speakers | 600 | 2400 | Gaming company owns
4 | ea | ultimate stands | 200 | 800 | Gaming company owns
4 | ea | speakon cable | 100 | 400 | Gaming company owns
1 | ea | sound mixer | 350 | 350 | Gaming company owns
8 | ea | XLR cable 25'-0" | 30 | 240 | Gaming company owns
2 | ea | Projector | 500 | 1000 | Gaming company owns
2 | ea | HDMI cable 30' | 100 | 200 | Gaming company owns
1 | ea | Video switcher | 400 | 400 | Gaming company owns
6 | ea | table 3x6 | 40 | 240 | Gaming company owns
5 | ea | table clothes fitted | 60 | 300 | Gaming company owns
16 | ea | truss: 12 box 8 ft tall | 300 | 4800 | Gaming company owns
2 | ea | truss: 12" box 8 ft tall | 300 | 600 | Gaming company owns
1 | ea | truss hardward | 200 | 200 | Gaming company owns
4 | ea | Truss base | 200 | 800 | Gaming company owns
2 | ea | Projector mount to truss | 100 | 200 | Gaming company owns
2 | ea | RP screen | 400 | 800 | Gaming company owns
1 | ea | bubble wrap | 150 | 150 | Gaming company owns
5 | ea | road box | 100 | 500 | Gaming company owns
2 | ea | glass cleaner | 20 | 40 | Gaming company owns
12 | ea | wipes | 20 | 240 | Gaming company owns
16 | ea | stanchions | 150 | 2400 | Gaming company owns
15 | ea | stanchion ropes | 200 | 3000 | Gaming company owns
1 | box | COVID signs and stickers | 100 | 100 | Gaming company owns
5 | ea | Camera Tripod | 25 | 125 | Gaming company owns
$ -
|  |  | Subtotal: | 28405
|  |  | 5% Hardware Estimate: | 1420.25
|  |  | Subtotal: | 29825.25
|  |  | 10% Contingency: | 2982.53
|  |  | Total: | 32807.78

## TD labor
Gaming project
|  | Prepared by: | TD
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | date | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meet with client | 2020-04-01 | 1 | 3 | 3 | 25 | 75
preparing bid documents | 2020-04-02 | 1 | 6 | 6 | 25 | 150
hire crew | 2020-04-03 | 1 | 8 | 8 | 25 | 200
Tour display design | 2020-04-07 | 1 | 6 | 6 | 25 | 150
soft test with local gear | 2020-04-08 | 1 | 6 | 6 | 25 | 150
order materials | 2020-04-15 | 1 | 2 | 2 | 25 | 50
build electrical system | 2020-04-21 | 1 | 8 | 8 | 25 | 200
build sound and light sytem | 2020-04-21 | 1 | 2 | 2 | 25 | 50
build game system | 2020-04-21 | 1 | 8 | 8 | 25 | 200
test game system | 2020-04-25 | 1 | 8 | 8 | 25 | 200
test sound and lights | 2020-04-25 | 1 | 2 | 2 | 25 | 50
integrate systems | 2020-04-28 | 1 | 4 | 4 | 25 | 100
soft opening gaming session | 2020-05-01 | 1 | 4 | 4 | 25 | 100
prep gear for tour | 2020-05-05 | 1 | 8 | 8 | 25 | 200
load truck | 2020-05-10 | 1 | 2 | 2 | 25 | 50
unload truck | 2020-05-14 | 1 | 2 | 2 | 25 | 50
load in event | 2020-05-14 | 1 | 4 | 4 | 25 | 100
tech event | 2020-05-14 | 1 | 3 | 3 | 25 | 75
run event | 2020-05-14 | 1 | 8 | 8 | 25 | 200
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 40 | 0
|  |  | Subtotal: | 94 |  | 2350
|  |  | 10% Contingency: | 9.4 |  | 235
|  |  | Total: | 103.4 |  | 2585

## TD load out labor
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
truck pack planning | 1 | 2 | 2 | 25 | 50
supervise crew | 1 | 4 | 4 | 25 | 100
park truck at secure locations | 1 | 2 | 2 | 25 | 50
|  |  | 0 | 25 | 0
|  | Subtotal: | 8 |  | 200
|  | 10% Contingency: | 0.8 |  | 20
|  | Total: | 8.8 |  | 220

## Weekly Update Labor plan
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
ELEMENT: | Tech labor
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
|  |  |  | 0 | 20 | 0
|  |  |  | 0 | 20 | 0
|  |  |  | 0 | 20 | 0
|  |  |  | 0 | 20 | 0
|  |  |  | 0 | 20 | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0
I suggest you cut and paste this page into the weekily location page
besure to update the totals pages for the location of the cost totals and person hours totals on your totals page

## voorhees
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0

## new theatre lobby
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0

## park slope
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0

## here
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0

## signature
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
[5 empty] | 25 | 0
[5 empty] | 25 | 0
[5 empty] | 25 | 0
[5 empty] | 25 | 0
[5 empty] | 25 | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0

## St Johns
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | skill | Number of Hours | Person Hours | Labor Rate | Cost
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 | 25 | 0
|  |  |  | 0 |  | 0
|  |  | Subtotal: | 0 |  | 0
|  |  | 10% Contingency: | 0 |  | 0
|  |  | Total: | 0 |  | 0

## Obstacle materials
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## Obstacle labor
Gaming Project | MTEC
Team name |  | Team members
Monopoly |  | Sarah
Tom
Date |  | Hanna
Prepared by |  | Mary
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0