## Totals sheet
Game Project | PM Sue Brandt
Labor | Person hours | description | auto-fill
Project Manager | 308 | Total==$25 X hrs | 12320
Developer Labor | 0 | Total==$25 X hrs | 0
IT Labor | 0 | Total==$25 X hrs | 0
Asset Labor | 136.4 | Total==$25 X hrs | 3410
Coding labor | 0 | Total==$25 X hrs | 0
Graphic art labor |  | Total==$25 X hrs | 2750
Subtotal | 110 | Subtotal | 18480
Materials |  | description | auto-fill
IT lab |  |  | 10164
developer |  |  | 0
coding |  |  | 0
asset |  |  | 0
graphics |  |  | 0
|  | Subtotal | 10164
transferring data teaching website
Labor total |  |  | 18480 | http://ccm.net/faq/9795-transfer-data-between-excel-spreadsheets
Matrials total |  |  | 10164
Person hours total |  |  | 110

## Gant planning
Game Project | PM Sue Brandt
| task | Start date | End date | duration/days
| meet with client | 2022-06-01 | 2022-06-04 | 3
| meet with team | 2022-06-05 | 2022-07-10 | 35
| coordinate teams | 2022-06-10 | 2022-06-12 | 2
| testing | 2022-06-13 | 2022-06-19 | 6
| presentation | 2022-06-20 | 2022-06-27 | 7
| create list of materials | 2022-06-10 | 2022-06-12 | 2
| build lab | 2022-06-13 | 2022-06-19 | 6
| maintain lab | 2022-06-20 | 2022-06-27 | 7
| build online locations | 2022-06-16 | 2022-07-21 | 35
| maintain online locations | 2022-06-15 | 2022-07-21 | 36
| test | 2022-06-16 | 2022-06-20 | 4
| update | 2022-06-21 | 2022-06-22 | 1
| test | 2022-06-23 | 2022-06-28 | 5
| update | 2022-07-11 | 2022-07-16 | 5
| test | 2022-07-17 | 2022-07-18 | 1
| demo | 2022-07-18 | 2022-07-24 | 6
| Draw and plan | 2022-06-10 | 2022-06-12 | 2
| proto types | 2022-06-13 | 2022-06-19 | 6
| update | 2022-06-20 | 2022-06-27 | 7
| update | 2022-06-11 | 2022-06-22 | 11
| update | 2022-06-23 | 2022-06-28 | 5
| update | 2022-07-11 | 2022-07-14 | 3
| demo | 2022-07-17 | 2022-07-18 | 1

## computer lab materials
Game Project | PM Sue Brandt
Prepared by:
Date:
Scenery
Quantity | Unit | Material | Unit Cost | Extended Cost
2 | ea | Mac book pro |  | 0
2 | ea | lenovo PC |  | 0
2 | ea | mouse for mac book pro |  | 0 | Total Cloud Cost (TC) = Service You Select (S) x Unit Price You Pay (P) x Volume You Use (V)
2 | ea | Mouse for PC |  | 0
4 | ea | Stream deck |  | 0
2 | seat | unity pro | 2400 | 4800
4 | 6 monthes | adobe creative cloud | 600 | 2400
4 | 6 monthes | cloud service | 400 | 1600
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 8800
|  |  | 5% Hardware Estimate: | 440
|  |  | Subtotal: | 9240
|  |  | 10% Contingency: | 924
|  |  | Total: | 10164

## PM labor
Game Project | PM Sue Brandt
Prepared by:
Date:
ELEMENT:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Meet with clients | 1 | 20 | 20 | 40 | 800
Draw and plan | 1 | 40 | 40 | 40 | 1600
hire team | 1 | 80 | 80 | 40 | 3200
order materials | 1 | 20 | 20 | 40 | 800
supervise team | 1 | 120 | 120 | 40 | 4800
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 280 |  | 11200
|  | 10% Contingency: | 28 |  | 1120
|  | Total: | 308 |  | 12320

## IT labor
Game Project | PM Sue Brandt
Prepared by:
Date:
Scenery labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meet with PM |  |  | 0 | 25 | 0
Meet with team |  |  | 0 | 25 | 0
create list of materials |  |  | 0 | 25 | 0
build lab |  |  | 0 | 25 | 0
maintain lab |  |  | 0 | 25 | 0
build online locations |  |  | 0 | 25 | 0
maintain online locations |  |  | 0 | 25 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## developer labor
Game Project | PM Sue Brandt
Prepared by:
Date:
control labor
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meet with team |  |  | 0 | 25 | 0
Draw and plan |  |  | 0 | 25 | 0
proto type |  |  | 0 | 25 | 0
test |  |  | 0 | 25 | 0
update |  |  | 0 | 25 | 0
test |  |  | 0 | 25 | 0
update |  |  | 0 | 25 | 0
test |  |  | 0 | 25 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## Asset labor
Game Project | PM Sue Brandt
Prepared by:
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meet with team | 2 | 20 |  | 25 | 0
determine assets needs | 2 | 12 | 24 | 25 | 600
proto type | 2 | 20 | 40 | 25 | 1000
test | 2 | 10 | 20 | 25 | 500
update | 2 | 20 | 40 | 25 | 1000
test |  | 10 | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 124 |  | 3100
|  | 10% Contingency: | 12.4 |  | 310
|  | Total: | 136.4 |  | 3410

## Graphic artist labor
Game Project | PM Sue Brandt
Prepared by:
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Meet with clients | 1 | 20 | 20 | 25 | 500
Draw and plan | 1 | 20 | 20 | 25 | 500
proto types | 1 | 20 | 20 | 25 | 500
update | 1 | 8 | 8 | 25 | 200
update | 1 | 8 | 8 | 25 | 200
update | 1 | 8 | 8 | 25 | 200
update | 1 | 8 | 8 | 25 | 200
update | 1 | 8 | 8 | 25 | 200
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 100 |  | 2500
|  | 10% Contingency: | 10 |  | 250
|  | Total: | 110 |  | 2750

## Coding labor
Game Project | PM Sue Brandt
Prepared by:
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meet with team |  |  | 0 | 25 | 0
determine game needs |  |  | 0 | 25 | 0
proto type |  |  | 0 | 25 | 0
test |  |  | 0 | 25 | 0
update |  |  | 0 | 25 | 0
test |  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  |  | 0 |  | 0
|  | Subtotal: | 0 |  | 0
|  | 10% Contingency: | 0 |  | 0
|  | Total: | 0 |  | 0

## Developer materials
Game Project | PM Sue Brandt
Prepared by:
Date:
Control materials
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## coding materials
Game Project | PM Sue Brandt
Prepared by:
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## Asset materials
Game Project | PM Sue Brandt
Prepared by:
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0

## Graphics Materials
Game Project | PM Sue Brandt
Prepared by:
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
|  | pen |  | 0
|  | pensil |  | 0
|  | paper |  | 0
|  | clay |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 0
|  |  | 5% Hardware Estimate: | 0
|  |  | Subtotal: | 0
|  |  | 10% Contingency: | 0
|  |  | Total: | 0