## Totals
Pop up event estimate |  |  | Prepared by:
Date:
Materials |  |  | Fill-in
Preproduction |  |  | 2.31
Production |  |  | 4.62
Postproduction |  |  | 697.62
Total cost
totals |  | total | 704.55
(Subtotal)
Labor | Person hours |  | Fill-in
Project Manager | 39.6 |  | 990
Preproduction | 85.8 | Total==$25 X hrs | 2145
Production | 23.1 | Total==$25 X hrs | 577.5
Postproduction | 19.8 | Total==$25 X hrs | 495
Total labor | 168.3 | total cost | 4207.5
Subtotal
Totals |  | Break down chart | Fill-in
Total materials |  |  | 704.55
Total man hours | 105.6
Total labor cost |  |  | 4207.5
Total cost |  |  | 4912.05

## preproduction labor
Preproduction labor |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Meet with clients | 1 | 6 | 6 | 25 | 150
build team | 1 | 8 | 8 | 25 | 200
hire team | 1 | 4 | 4 | 25 | 100
research costs | 1 | 4 | 4 | 25 | 100
buy materials | 1 | 16 | 16 | 25 | 400
build booth | 1 | 40 | 40 | 25 | 1000
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 78 |  | 1950
|  | 10% Contingency: | 7.8 |  | 195
|  | Total: | 85.8 |  | 2145

## schedule
Campaign project |  |  | Prepared by: | PM Sue Brandt
Date:
Gantt Table
start date | End Date | task | duration
2024-01-31 | 2024-05-20 | Production meetings | 110
2024-02-07 | 2024-02-14 | create a communications plan | 7
2024-02-14 | 2024-02-21 | Create a marketing plan | 7
2024-02-21 | 2024-02-28 | Safety analysis | 7
2024-03-15 | 2024-03-22 | charts GANT, PERT and WBS | 7
2024-03-06 | 2024-03-15 | estimate | 9
2024-03-08 | 2024-05-08 | Production | 61
2024-03-18 | 2024-04-02 | load in | 15
2024-04-03 | 2024-04-15 | Tech | 12
2024-05-05 | 2024-05-07 | Performance | 2
2024-05-08 | 2024-05-10 | strike | 2
2024-05-18 | 2024-05-19 | post production review | 1

## PM labor
Campaign project PM |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
Production meetings | 1 | 21 | 21 | 25 | 525
create a communications plan | 1 | 3 | 3 | 25 | 75
Create a marketing plan | 1 | 4 | 4 | 25 | 100
Safety analysis | 1 | 2 | 2 | 25 | 50
charts GANT, PERT and WBS | 1 | 3 | 3 | 25 | 75
estimate | 1 | 3 | 3 | 25 | 75
Production | 1 |  | 0 | 25 | 0
load in | 1 |  | 0 | 25 | 0
Tech | 1 |  | 0 | 25 | 0
Performance | 1 |  | 0 | 25 | 0
strike | 1 |  | 0 | 25 | 0
post production review | 1 |  | 0 | 25 | 0
| 1 |  | 0 | 25 | 0
| 1 |  | 0 | 25 | 0
|  | Subtotal: | 36 |  | 900
|  | 10% Contingency: | 3.6 |  | 90
|  | Total: | 39.6 |  | 990

## preproduction materals
Pre-production materials |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
1 | ea | bindefr | 2 | 2
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 2
|  |  | 5% Hardware Estimate: | 0.1
|  |  | Subtotal: | 2.1
|  |  | 10% Contingency: | 0.21
|  |  | Total: | 2.31

## production labor
production labor |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
load in. | 2 | 2 | 4 | 25 | 100
set up | 2 | 2 | 4 | 25 | 100
test | 1 | 1 | 1 | 25 | 25
run event | 1 | 6 | 6 | 25 | 150
close | 2 | 1 | 2 | 25 | 50
strike | 2 | 2 | 4 | 25 | 100
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 21 |  | 525
|  | 10% Contingency: | 2.1 |  | 52.5
|  | Total: | 23.1 |  | 577.5

## production materials
Pre-production materials |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
2 | ea | binder | 2 | 4
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 4
|  |  | 5% Hardware Estimate: | 0.2
|  |  | Subtotal: | 4.2
|  |  | 10% Contingency: | 0.42
|  |  | Total: | 4.62

## post production labor
post production labor |  |  | Prepared by: | PM Sue Brandt
Date:
Procedure: | Number of Crew | Number of Hours | Person Hours | Labor Rate | Cost
meeting | 4 | 2 | 8 | 25 | 200
rebuild | 4 | 2 | 8 | 25 | 200
store gear | 2 | 1 | 2 | 25 | 50
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  |  | 0 | 25 | 0
|  | Subtotal: | 18 |  | 450
|  | 10% Contingency: | 1.8 |  | 45
|  | Total: | 19.8 |  | 495

## post production materials
Postproduction materials |  |  | Prepared by: | PM Sue Brandt
Date:
Quantity | Unit | Material | Unit Cost | Extended Cost
2 | ea | binder | 2 | 4
3 | ea | storate | 200 | 600
0
0
0
0
0
0
0
0
0
0
0
|  |  | Subtotal: | 604
|  |  | 5% Hardware Estimate: | 30.2
|  |  | Subtotal: | 634.2
|  |  | 10% Contingency: | 63.42
|  |  | Total: | 697.62