Justin Rivera

ENT4499-D286

Proposal

**Scope**: I would like to change the direction of Culmination project. Originally I wanted to work with microphones, but now I want to do something more creative. I want to make my own music and create an EP/mixtape. During my time at City Tech and QueensBorough, I’ve been focusing more on the engineering side. Now however, I want to challenge myself think in a way I never thought before. I’ve always wanted to be a music producer growing up, and now seems like the best opportunity to do so. My plan is to make original music, with time sheets, and have local artists to sing/rap on them. I plan on making 4 tracks covering a few music genders, from hip hop to pop. All the music, recording, and mastering will be done by me, and the artists will have the freedom to write their own lyrics. I will also make time sheets for each song, indicating verse, chorus, hook, etc. etc. As well as, the instruments being used .By the time I’m finish I plan on having a 4 track EP that I could hopefully show potential artists/clients in the future.

**Materials needed:**

Shure SM58 - $100

Audio-Technica BP4002 - $149

Avid Pro Tools + MBox Pro $999

Desktop - $500

M-Audio AV 40 monitors - $149

**Total Materials:** $1,897

**Milestones Calendar**

**10/6/15 – 10/10/15:** Finishing producing all tracks

**10/11/15:** Make Time sheets

**10/12/15:** Have meeting with all artist going over the time sheets, and potential lyrics

**10/14/15:** Record track 1

**10/16/15**: Record track 2

**10/17/15:** Record track 3

**10/18/15**: Record track 4

**10/19/15-10/21/15** – Mix/Master all tracks

**10/23/15**: Get feedback from artists

**10/25/15:** Finish