## Milestones
Milestones | DATE
Deck BUDGET APPROVED | 2014-10-01
Deck PURCHASING COMPLETE | 2014-10-03
Haunted Hotel TECH BEGINS | 2014-10-11
Deck BUILD DAY | 2014-10-14
Deck BUILD DAY | 2014-10-16
Deck BUILD DAY | 2014-10-18
Deck BUILD DAY | 2014-10-21
Deck BUILD DAY | 2014-10-23
Deck BUILD DAY | 2014-10-25
Deck BUILD DAY | 2014-10-28
Deck BUILD DAY | 2014-10-30
Deck BUILD DAY | 2014-11-01
Haunted Hotel CLOSES | 2014-11-02
Haunted Hotel LOAD-OUT BEGINS | 2014-11-03
Haunted Hotel LOAD-OUT COMPLETE | 2014-11-06
Deck WORK CALL | 2014-11-07
Deck PAINT CALL | 2014-11-07
Deck LIGHT HANG | 2014-11-08
Deck LAYOUT | 2014-11-10
Deck CARP LOAD-IN | 2014-11-11
Deck SCENIC CALL | 2014-11-11
Deck LIGHT FOCUS | 2014-11-13
CONCERT | 2014-11-14
TALENT SHOW | 2014-11-15

## Month View
OCTOBER | 2014 |  |  | 10
October & November 2014
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  |  | 1 | 2 | 3 | 4
|  |  | Deck BUDGET APPROVED |  | Deck PURCHASING
5 | 6 | 7 | 8 | 9 | 10 | 11
Haunted Hotel TECH BEGINS
12 | 13 | 14 | 15 | 16 | 17 | 18
|  | Deck BUILD DAY |  | Deck BUILD DAY |  | Deck BUILD DAY
TBD
19 | 20 | 21 | 22 | 23 | 24 | 25
|  | Deck BUILD DAY |  | Deck BUILD DAY |  | Deck BUILD DAY
TBD
26 | 27 | 28 | 29 | 30 | 31 | 1
|  | Deck BUILD DAY |  | Deck BUILD DAY | Halloween! | Deck BUILD DAY
TBD
2 | 3 | 4 | 5 | 6 | 7 | 8
Haunted Hotel CLOSES | Haunted Hotel LOAD-OUT | __________________________________________ | ________________________________ | LOAD-OUT COMPLETE | Deck WORK CALL | Deck LIGHT HANG
Deck PAINT CALL
9 | 10 | 11 | 12 | 13 | 14 | 15
| Deck LAYOUT | Deck CARP LOAD-IN |  | Deck LIGHT FOCUS | CONCERT | TALENT SHOW
Deck SCENIC CALL

## Week View
MARCH | 2013 | WEEK 6 | 6 | 3
WEEK VIEW
[5 empty] | 1 | 2
3 | 4 | 5 | 6 | 7 | 8 | 9
10 | 11 | 12 | 13 | 14 | 15 | 16
17 | 18 | 19 | 20 | 21 | 22 | 23
24 | 25 | 26 | 27 | 28 | 29 | 30
31
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
24 | 25 | 26 | 27 | 28 | 29 | 30
31