## Milestones
Milestones Calendar | DATE
Deck BUDGET APPROVED | 2014-10-01
Deck PURCHASING COMPLETE | 2014-10-03
Haunted Hotel TECH BEGINS | 2014-10-11
Deck BUILD DAY | 2014-10-14
Deck BUILD DAY | 2014-10-16
Deck BUILD DAY | 2014-10-18
Deck BUILD DAY | 2014-10-21
Deck BUILD DAY | 2014-10-23
Deck BUILD DAY | 2014-10-25
Deck BUILD DAY | 2014-10-28
Deck BUILD DAY | 2014-10-30
Deck BUILD DAY | 2014-11-01
Haunted Hotel CLOSES | 2014-11-02
Haunted Hotel LOAD-OUT BEGINS | 2014-11-03
Haunted Hotel LOAD-OUT COMPLETE | 2014-11-06
Deck WORK CALL | 2014-11-07
Deck PAINT CALL | 2014-11-07
Deck LIGHT HANG | 2014-11-08
Deck LAYOUT | 2014-11-10
Deck CARP LOAD-IN | 2014-11-11
Deck SCENIC CALL | 2014-11-11
Deck LIGHT FOCUS | 2014-11-13
CONCERT | 2014-11-14
TALENT SHOW | 2014-11-15

## Labor Budget
Labor Budget
CALL | DATE | PRODUCTION CLASS (Y/N) | # CREW | LENGTH OF CALL (hours) | MAN HOURS | NOTES
Deck BUILD DAY | 2014-10-14 | Y | 6 | 2 | 12
Deck BUILD DAY | 2014-10-16 | Y | 6 | 2 | 12
Deck BUILD DAY | 2014-10-18 | N | 3 | 4 | 12 | TBD by Master Carp based on week's shop work
Deck BUILD DAY | 2014-10-21 | Y | 8 | 2 | 16
Deck BUILD DAY | 2014-10-23 | Y | 8 | 2 | 16
Deck BUILD DAY | 2014-10-25 | N | 3 | 4 | 12 | TBD by Master Carp based on week's shop work
Deck BUILD DAY | 2014-10-28 | Y | 8 | 2 | 16
Deck BUILD DAY | 2014-10-30 | Y | 8 | 2 | 16
Deck BUILD DAY | 2014-11-01 | N | 3 | 4 | 12 | TBD by Master Carp basded on week's shop work
Haunted Hotel CLOSES | 2014-11-02
Haunted Hotel LOAD-OUT BEGINS | 2014-11-03 |  |  |  |  | FOR REFERENCE ONLY
Haunted Hotel LOAD-OUT COMPLETE | 2014-11-06
Deck WORK CALL | 2014-11-07 | N | 4 | 2 | 8 | Lay Maso floor
Deck PAINT CALL | 2014-11-07 | N | 4 | 2 | 8 | Paint Floor Black
Deck LIGHT HANG | 2014-11-08 | N | 2 | 4 | 8 | TBD for Carps
Deck LAYOUT | 2014-11-10 | N | 4 | 2 | 8 | Loacate refrence points on floor for LOAD-IN
Deck CARP LOAD-IN | 2014-11-11 | Y | 8 | 2 | 16 | Install Deck
Deck SCENIC CALL | 2014-11-11 | N | 4 | 2 | 8 | Paint Logo for Band
Deck LIGHT FOCUS | 2014-11-13 | Y | 8 | 2 | 16 | Production Class so Carps will work around Light Focus doing finish work
CONCERT | 2014-11-14 | N | 10 | 6 | 60 | Finish work/Tech/Show/Post Show (Marley layout)
TALENT SHOW | 2014-11-15 | N | 5 | 10 | 50 | Marley Layout cont(TBD)/tech/Show
|  |  |  | total man hours | 306
|  |  | total class man hours |  | 120
NOTES:
Production Class carpentry crew to be used as labor pool during Tech Production class times, outside calls to be filled by any/all voulenteers
Produciton Carp Crew consisits of 8-10 people with some Haunted Hotel obligations therefore we have lowballed out labor projection but scheduled TBD calls to keep on schedule

## Materials List
Materials List
Material | Specs | # of Units | Unit Price | Price | Vendor
Black Paint | Valspar Satin Porch & Floor Paint, 1 gallon | 10 | 28.58 | 285.8 | Lowes
Roller covers | Wooster 6-Pack 9-in x .37-in High Capacity Roller Covers | 2 | 12.99 | 25.98 | Lowes
Roller cages | Blue Hawk 14-in Metal Paint Roller Frame | 3 | 5.98 | 17.94 | Lowes
Paint Trays |  | 2 | N/A | N/A | IN STOCK AT CITY TECH
Marley | Bellare Glossy Floor, Black, Roll 59" wide | 1 | 1225 | 1225 | Rosebrand
Marley Tape | clear dance floor tape, 36yrds | 3 | 7.35 | 22.05 | Rosebrand
Paint For Band Logo | Rosco Supersaturated, quart (3 colors) | 3 | 20 | 60 | Rosebrand
0
0
0
0
0
0
0
0
0
0
0
0

## Month View
OCTOBER | 2014 |  |  | 10
October & November 2014
SUNDAY | MONDAY | TUESDAY | WEDNESDAY | THURSDAY | FRIDAY | SATURDAY
|  |  | 1 | 2 | 3 | 4
|  |  | Deck BUDGET APPROVED |  | Deck PURCHASING
5 | 6 | 7 | 8 | 9 | 10 | 11
Haunted Hotel TECH BEGINS
12 | 13 | 14 | 15 | 16 | 17 | 18
|  | Deck BUILD DAY |  | Deck BUILD DAY |  | Deck BUILD DAY
TBD
19 | 20 | 21 | 22 | 23 | 24 | 25
|  | Deck BUILD DAY |  | Deck BUILD DAY |  | Deck BUILD DAY
TBD
26 | 27 | 28 | 29 | 30 | 31 | 1
|  | Deck BUILD DAY |  | Deck BUILD DAY | Halloween! | Deck BUILD DAY
TBD
2 | 3 | 4 | 5 | 6 | 7 | 8
Haunted Hotel CLOSES | Haunted Hotel LOAD-OUT | __________________________________________ | ________________________________ | LOAD-OUT COMPLETE | Deck WORK CALL | Deck LIGHT HANG
Deck PAINT CALL
9 | 10 | 11 | 12 | 13 | 14 | 15
| Deck LAYOUT | Deck CARP LOAD-IN |  | Deck LIGHT FOCUS | CONCERT | TALENT SHOW
Deck SCENIC CALL

## Sheet4
Event Calendar