|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **June**  Lighting Crew  Scenic Crew Theatre  Paint Crew | | | | | |  | |
| **SUNDAY** | | **MONDAY** | **TUESDAY** | **WEDNESDAY** | **THURSDAY** | **FRIDAY** | **SATURDAY** |
|  | 28 | **29** | **30** | **31** | **1** | **2** | 3 |
|  | |  |  |  |  |  |  |
|  | 4 | **5** | **6** | **7** | **8** | **9** | 10 |
|  | |  |  |  |  |  |  |
|  | 11 | **12** | **13** | **14** | **15** | **16** | 17 |
|  | |  | 10 AM – 4 PM  Cutlists/Construction Drawings Half Crew | 10 AM – 4 PM Cutlists/Revisions  Half Crew | 10 AM – 6 PM Rigging Install  Full Crew | 10 AM – 6 PM Rigging Install  Full Crew |  |
|  | 18 | **19** | **20** | **21** | **22** | **23** | 24 |
|  | | 10 AM – 6 PM Scenic Build  Full Crew | 10 AM – 6 PM Scenic Build  Full Crew | 10 AM – 6 PM Scenic Build Full Crew | 10 AM – 6 PM Paint Crew Full Crew | 10 AM – 6 PM Paint Crew Full Crew |  |
|  | 25 | **26** | **27** | **28** | **29** | **30** | 1 |
|  | | 10 AM – 6 PM Assembly Build Full Crew | 10 AM – 6 PM Assembly Build Full Crew  6 PM – 10 PM Lighting Crew A/V | 10 AM – 4 PM Production Notes  Half Crew | 10 AM – 4 PM Production Notes  Half Crew | 4 PM Tech Rehearsals  Full Crew | 4 PM Tech Rehearsals  Full Crew  8 PM Show |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **July** | | | | | | |  |  |  |  |  |  |  | | --- | --- | --- | --- | --- | --- | --- | |  | | | | | | | |  |  |  |  |  |  |  | |  |  |  |  |  |  |  | |  |  |  |  |  |  |  | |  |  |  |  |  |  |  | |  |  |  |  |  |  |  | |  |  |  |  |  |  |  | |  |  |  |  |  |  |  | | |
| **SUNDAY** | | **MONDAY** | **TUESDAY** | **WEDNESDAY** | **THURSDAY** | **FRIDAY** | **SATURDAY** |
|  | 25 | **26** | **27** | **28** | **29** | **30** | 1 |
|  | | 10 AM – 6 PM Assembly Build Full Crew | 10 AM – 6 PM Assembly Build Full Crew  6 PM – 10 PM Lighting Crew A/V | 10 AM – 4 PM Production Notes  Half Crew | 10 AM – 4 PM Production Notes  Half Crew | 4 PM Tech Rehearsals  Full Crew | 4 PM Tech Rehearsals  Full Crew  8 PM Show |
|  | 2 | **3** | **4** | **5** | **6** | **7** | 8 |
|  | |  |  |  |  |  |  |
|  | 9 | **10** | **11** | **12** | **13** | **14** | 15 |
|  | |  |  |  |  |  |  |
|  | 16 | **17** | **18** | **19** | **20** | **21** | 22 |
|  | |  |  |  |  |  |  |
|  | 23 | **24** | **25** | **26** | **27** | **28** | 29 |
|  | |  |  |  |  |  |  |
|  | 30 | **31** | **1** | **2** | **3** | **4** | 5 |
|  | |  |  |  |  |  |  |

Hourly Pay for Senic Crew:

Stagehands: $20/hr

Technical Director: $55/hr

Scenic Artist: $25/hr

July 13th 6 Hour Call July 14th 6 Hour Call July 15th 8 Hour Call July 16th 8 Hour Call

Stagehand Members: $480 Stagehand Members: $480 Stagehand Members: $1,280 Stagehand Members: $1,280

Name 1: $120 Name 1: $120 Name 1: $160 Name 1: $160

Name 2: $120 Name 2: $120 Name 2: $160 Name 2: $160

Name 3: $120 Name 3: $120 Name 3: $160 Name 3: $160

Name 4: $120 Name 4: $120 Name 4: $160 Name 4: $160

Name 5: $160 Name 5: $160

Technical Director: $330 Technical Director: $330 Name 6: $160 Name 6: $160

Name 7: $160 Name 7: $160

Name 8: $160 Name 8: $160

Technical Director: $440 Technical Director: $440

July 19th 8 Hour Call July 20th 8 Hour Call July 21st 8 Hour Call July 22nd 8 Hour Call

Stagehand Members: $1,280 Stagehand Members: $1,280 Stagehand Members: $1,280 Stagehand Members: $1,280

Name 1: $160 Name 1: $160 Name 1: $160 Name 1: $160

Name 2: $160 Name 2: $160 Name 2: $160 Name 2: $160

Name 3: $160 Name 3: $160 Name 3: $160 Name 3: $160

Name 4: $160 Name 4: $160 Name 4: $160 Name 4: $160

Name 5: $160 Name 5: $160 Name 5: $160 Name 5: $160

Name 6: $160 Name 6: $160 Name 6: $160 Name 6: $160

Name 7: $160 Name 7: $160 Name 7: $160 Name 7: $160

Name 8: $160 Name 8: $160 Name 8: $160 Name 8: $160

Technical Director: $440 Technical Director: $440 Technical Director: $440 Scenic Artist: $200

July 23rd 8 Hour Call July 26th 8 Hour Call July 27th 8 Hour Call July 28th 6 Hour Call

Stagehand Members: $1,280 Stagehand Members: $1,280 Stagehand Members: $1,280 Stagehand Members: $480

Name 1: $160 Name 1: $160 Name 1: $160 Name 5: $120

Name 2: $160 Name 2: $160 Name 2: $160 Name 6: $120

Name 3: $160 Name 3: $160 Name 3: $160 Name 7: $120

Name 4: $160 Name 4: $160 Name 4: $160 Name 8: $120

Name 5: $160 Name 5: $160 Name 5: $160

Name 6: $160 Name 6: $160 Name 6: $160 Technical Director $330

Name 7: $160 Name 7: $160 Name 7: $160

Name 8: $160 Name 8: $160 Name 8: $160

Scenic Artist: $200 Technical Director: $440 Technical Director $440

July 29th 6 Hour Call

Name 5: $120

Name 6: $120

Name 7: $120

Name 8: $120

Technical Director $330